## Ips GC Sch 24 8 wk
Ward | 1st cut | 2nd cut | 3rd cut
Rushmere | w/c 18th March 2024 (5 days) | w/c 27th May (4 days + Bank Holiday) | w/c 5th August 2024 (5 days)
St Margarets | w/c 18th March 2024 (5 days) | w/c 27th May (4 days + Bank Holiday) | w/c 5th August 2024 (5 days)
Castle Hill | w/c 25th March 2024 (4 days + Bank Holiday) | w/c 3rd June 2024 (5 days) | w/c 12th August 2024 (5 days)
Whitton | w/c 25th March 2024 (4 days + Bank Holiday) | w/c 3rd June 2024 (5 days) | w/c 12th August 2024 (5 days)
Whitehouse | w/c 1st April 2024 (4 days + Bank Holiday) | w/c 10th June 2024 (5 days) | w/c 19th August 2024 (5 days)
St Johns | w/c 8th April 2024 (5 days) | w/c 17th June 2024 (5 days) | w/c 26th August 2024 (4 days + Bank Holiday)
Alexandra | w/c 8th April 2024 (5 days) | w/c 17th June 2024 (5 days) | w/c 26th August 2024 (4 days + Bank Holiday)
Bixley | w/c 8th April 2024 (5 days) | w/c 17th June 2024 (5 days) | w/c 26th August 2024 (4 days + Bank Holiday)
Holywells | w/c 15th April 2024 (5 days) | w/c 24th June 2024 (5 days) | w/c 2nd Sept 2024 (5 days)
Stoke Park | w/c 15th April 2024 (5 days) | w/c 24th June 2024 (5 days) | w/c 2nd Sept 2024 (5 days)
Gipping | w/c 22nd April 2024 (5 days) | w/c 1st July 2024 (5 days) | w/c 9th Sept 2024 (5 days)
Sprites | w/c 22nd April 2024 (5 days) | w/c 1st July 2024 (5 days) | w/c 9th Sept 2024 (5 days)
Gainsborough | w/c 29th April 2024 (5 days) | w/c 8th July 2024 (5 days) | w/c 16th Sept 2024 (5 days)
Westgate | w/c 29th April 2024 (5 days) | w/c 8th July 2024 (5 days) | w/c 16th Sept 2024 (5 days)
Bridge | w/c 29th April 2024 (5 days) | w/c 8th July 2024 (5 days) | w/c 16th Sept 2024 (5 days)
Priory Heath | w/c 6th May (4 days +Bank Holiday) | w/c 15th July 2024 (5 days) | w/c 23rd Sept 2024 (5 days)
| 8 week program | 8 week program | 8 week program

## Ips GC Sch 24 b 8 wk
Date | w/c 18/03/24 | w/c 25/03/24 | w/c 01/04/24 | w/c 08/04/24 | w/c 15/04/24 | w/c 22/04/24 | w/c 29/04/24 | w/c 06/05/2024 | w/c 13/05/2024 | w/c 20/05/2024 | w/c 27/05/2024 | w/c 03/06/24 | w/c 10/06/24 | w/c 17/06/24 | w/c 24/06/24 | w/c 01/07/24 | w/c 08/07/24 | w/c 15/07/24 | w/c 22/07/24 | w/c 29/07/24 | w/c 05/08/24 | w/c 12/08/24 | w/c 19/08/24 | w/c 26/08/24 | w/c 02/09/24 | w/c 09/09/24 | w/c 16/09/24 | w/c 23/09/24 | w/c 30/09/24
Ward / No of week days | 5 days | 4 days + Bank Holiday | 4 days + Bank Holiday | 5 days | 5 days | 5 days | 5 days | 4 days | 5 days | 5 days | 4 days | 5 days | 5 days | 5 days | 5 days | 5 days | 5 days | 5 days | 5 days | 5 days | 5 days | 5 days | 5 days | 4 days + Bank Holiday | 5 days | 5 days | 5 days | 5 days | 5 days
Rushmere | ☑ | [9 empty] | ☑ | [9 empty] | ☑
St Margarets | ☑ | [9 empty] | ☑ | [9 empty] | ☑
Castle Hill |  | ☑ | [9 empty] | ☑ | [9 empty] | ☑
Whitton |  | ☑ | [9 empty] | ☑ | [9 empty] | ☑
Whitehouse |  |  | ☑ | [9 empty] | ☑ | [9 empty] | ☑
St Johns |  |  |  | ☑ | [9 empty] | ☑ | [9 empty] | ☑
Alexandra |  |  |  | ☑ | [9 empty] | ☑ | [9 empty] | ☑
Bixley |  |  |  | ☑ | [9 empty] | ☑ | [9 empty] | ☑
Holywells |  |  |  |  | ☑ | [9 empty] | ☑ | [9 empty] | ☑
Stoke Park |  |  |  |  | ☑ | [9 empty] | ☑ | [9 empty] | ☑
Gipping | [5 empty] | ☑ | [9 empty] | ☑ | [9 empty] | ☑
Sprites | [5 empty] | ☑ | [9 empty] | ☑ | [9 empty] | ☑
Gainsborough | [6 empty] | ☑ | [9 empty] | ☑ | [9 empty] | ☑
Westgate | [6 empty] | ☑ | [9 empty] | ☑ | [9 empty] | ☑
Bridge | [6 empty] | ☑ | [9 empty] | ☑ | [9 empty] | ☑
Priory Heath | [7 empty] | ☑ | [9 empty] | ☑ | [9 empty] | ☑

## Sheet1
IPSWICH GRASS CUTTING PROGRAMME 2024
Ipswich Wards | Grass Cutting Target 1st Cut date (week commencing)
RUSHMERE | 18th March 2024 | COMPLETED (w/c 18/03/24)
ST MARGARETS | 18th March 2024 | COMPLETED (w/c 18/03/24)
CASTLE HILL | 25th March 2024 | COMPLETED (w/c 01/04/24)
WHITTON | 25th March 2024 | COMPLETED (w/c 01/04/24)
WHITEHOUSE | 1st April 2024 | COMPLETED (w/c 01/04/24)
ST JOHNS | 8th April 2024 | COMPLETED (w/c 08/04/24)
ALEXANDRA | 8th April 2024 | COMPLETED (w/c 08/04/24)
BIXLEY | 8th April 2024 | COMPLETED (w/c 08/04/24)
HOLYWELLS | 15th April 2024 | COMPLETED (w/c 15/04/24)
STOKE PARK | 15th April 2024 | COMPLETED (w/c 15/04/24)
GIPPING | 22nd April 2024 | COMPLETED (w/c 22/04/24)
SPRITES | 22nd April 2024 | COMPLETED (w/c 22/04/24)
GAINSBOROUGH | 29th April 2024 | COMPLETED (w/c 29/04/24)
WESTGATE | 29th April 2024 | COMPLETED (w/c 22/04/24)
BRIDGE | 29th April 2024 | COMPLETED (w/c 29/04/24)
PRIORY HEATH | 6th May 2024 | COMPLETED (w/c 29/04/24)
*Note: Actual Cut Dates shown in Green
*Note: Target Dates shown in white
*Note: Target Dates shown in yellow are Ongoing
Ipswich Wards | Grass Cutting Target 2nd Cut date (week commencing)
RUSHMERE | 27th May 2024
ST MARGARETS | 27th May 2024
CASTLE HILL | 3rd June 2024
WHITTON | 3rd June 2024
WHITEHOUSE | 10th June 2024
ST JOHNS | 17th June 2024
ALEXANDRA | 17th June 2024
BIXLEY | 17th June 2024
HOLYWELLS | 24th June 2024
STOKE PARK | 24th June 2024
GIPPING | 1st July 2024
SPRITES | 1st July 2024
GAINSBOROUGH | 8th July 2024
WESTGATE | 8th July 2024
BRIDGE | 8th July 2024
PRIORY HEATH | 15th July 2024
*Note: Actual Cut Dates shown in Green
*Note: Target Dates shown in white
*Note: Target Dates shown in yellow are Ongoing
Ipswich Wards | Grass Cutting Target 3rd Cut date (week commencing)
RUSHMERE | 5th August 2024
ST MARGARETS | 5th August 2024
CASTLE HILL | 12th August 2024
WHITTON | 12th August 2024
WHITEHOUSE | 19th August 2024
ST JOHNS | 26th August 2024
ALEXANDRA | 26th August 2024
BIXLEY | 26th August 2024
HOLYWELLS | 2nd September 2024
STOKE PARK | 2nd September 2024
GIPPING | 9th September 2024
SPRITES | 9th September 2024
GAINSBOROUGH | 16th September 2024
WESTGATE | 16th September 2024
BRIDGE | 16th September 2024
PRIORY HEATH | 23rd September 2024
*Note: Actual Cut Dates shown in Green
*Note: Target Dates shown in white
*Note: Target Dates shown in yellow are Ongoing