## Sheet1
Risk | Description | Impact | Probability | Rating | Mitigation
Consultation response | The project will require consultation and engagement with stakeholders and the public. A strong negative response could risk approval for the project to progress. | High | Unlikely | Medium | Continued engagement with relevant stakeholders throughout project
Cost changes | Inflationary impacts on project costs and services could cause delay and risk delivering the project. | High | Probable | High | Allocation of developer funding held by the council and the council's own funding to cover overspend
Design issues | Issues arising through detailed design such as road space availaibility, drainage and vehicle tracking could risk the delivery of elements of the package or the package as a whole. | High | Unlikely | Medium | Early warning process including regular meetings with the contractor to resolve issues as they arise
Statutory undertakers | Removal of roadside hazards relies on work undertaken by utility companies to relocate their equipment. Possible cost and programme risks associated 3rd party works. | Moderate | Unlikely | Low | Continued engagement with relevant utility companies throughout project
Delivery issues | Issues arising during the construction of the scheme such as environmentally sensitive areas, underground services and material avalibility could risk the delivery of elements of the package or the package as a whole | High | Unlikely | Medium | Early contractor involvment in the detailed design process and undertaking relevant surveys proportionate to the scale and nature of the scheme