## Sheet1
Cyclic Gully Cleansing Programme
Note: The following table provides a target start date for gully cleansing in each drainage zone, but gully cleansing activities can be affected by weather, excessive on-street parking or emergency callouts, so start dates may vary.
District or Borough | Drainage Zone | Parishes within Drainage Zone | Target start date | To be completed by (target)
Babergh and Mid Suffolk (Babergh)
Babergh | Alton | Tattingstone, Brantham, Stutton | 2025-04-01 | 2025-04-26
Babergh | Berners | Freston, Woolverstone, Chelmondiston, Arwarton, Shotley | 2025-04-15 | 2024-05-04
Babergh | Boxford | Milden, Lindsey, Edwardstone, Groton, Boxford | 2025-04-23 | 2025-05-07
Babergh | Brett Vale | Brettenham, Hitcham, Wattisham, Bildeston | 2025-04-28 | 2025-05-12
Babergh | Brook | Sproughton,Burstall,Hintlesham,Chattisham,Copdock and Washbrook, Belstead, Wherstead | 2025-04-01 | 2025-04-28
Babergh | Bures St Mary | Bures St Mary, Little Cornard, Newton | 2025-04-17 | 2025-05-05
Babergh | Chadacre | Lawshall, Shimpliing, Hartest, Somerton, Boxtead | 2025-04-24 | 2025-05-11
Babergh | Dodnash | Bentley, East Bergholt | 2025-04-01 | 2025-04-21
Babergh | Glemsford & Stanstead | Glemsford, Stanstead | 2025-04-10 | 2025-04-28
Babergh | Great Cornard North | split large parish Gt Cornard | 2025-04-17 | 2025-05-12
Babergh | Great Cornard South | split large parish Gt Cornard | 2025-04-17 | 2025-05-12
Babergh | Hadleigh North | split large parish Hadleigh | 2025-04-01 | 2025-04-22
Babergh | Hadleigh South | split large parish Hadleigh | 2025-04-11 | 2025-04-26
Babergh | Holbrook | Holbrook, Harkstead | 2024-04-15 | 2023-04-27
Babergh | Lavenham | Lavenham | 2025-05-01 | 2025-05-19
Babergh | Leavenheath | Leavenheath, Assington | 2025-05-08 | 2025-05-24
Babergh | Long Melford | Long Melford, Alpheton | 2025-05-13 | 2025-06-04
Babergh | Lower Brett | Polstead, Layham, Shelley, Raydon, Higham (East) | 2025-05-27 | 2025-06-10
Babergh | Mid Samford | Wenham Magna, Wenham Parva, Capel St Mary, Holton St Mary, Stratford St Mary | 2025-04-30 | 2025-05-26
Babergh | Nayland | Stoke by Nayland, Nayland with Wissington | 2025-05-15 | 2025-05-28
Babergh | North Cosford | Cockfield, Thorpe Morieux, Preston St Mary, Kettlebaston, Chelsworth, Monks Eleigh, Brent Eleigh | 2025-04-19 | 2025-06-10
Babergh | Pinewood | Pinewood | 2025-05-01 | 2025-05-19
Babergh | South Cosford | Kersey, Semer, Nedging with Naughton, Whatfield, Elmsett, Aldham | 2025-05-08 | 2025-05-21
Babergh | Sudbury East | split large parish Sudbury | 2025-05-12 | 2025-06-03
Babergh | Sudbury North | split large parish Sudbury | 2025-05-23 | 2025-06-15
Babergh | Sudbury South | split large parish Sudbury | 2025-05-29 | 2025-06-22
Babergh | Waldingfield | Little Waldingfield, Great Waldingfield, Chilton, Acton | 2025-06-11 | 2025-07-01
Babergh and Mid Suffolk (Mid Suffolk)
Mid Suffolk | Bacton & Old Newton | Bacton, Old newton with Dagworth, Gipping | 2025-05-30 | 2025-06-18
Mid Suffolk | Badwell Ash | Badwell Ash, Great Ashfield, Langham, Hunston, Stowlangtoft, Wyverstone, Westhorpe, Finningham | 2025-06-09 | 2025-06-25
Mid Suffolk | Barking & Somersham | Barking, Darmsden, Baylham, Nettlestead, Willisham, Offton, Somersham | 2005-06-16 | 2025-07-05
Mid Suffolk | Bramford & Blakenham | Great Blakenham, Little Blakenham, Flowton, Bramford | 2025-06-24 | 2025-07-16
Mid Suffolk | Claydon & Barham | Hemingstone, Barham, Henley, Claydon, Akenham, Shitton | 2025-05-30 | 2025-06-16
Mid Suffolk | Debenham | Debenham, Aspall, Winston | 2025-06-05 | 2025-06-24
Mid Suffolk | Elmswell & Norton | Norton, Elmswell, Tostock | 2025-06-13 | 2025-07-06
Mid Suffolk | Eye | Eye | 2025-06-25 | 2025-07-12
Mid Suffolk | Fressingfield | Mendham, Weybread, Metfield, Fressingfield | 2024-06-04 | 2025-06-21
Mid Suffolk | Gislingham | Wortham, Burgate, Mellis, Thornham Parva, Gislingham, Thornham Magna | 2025-06-10 | 2025-06-28
Mid Suffolk | Haughley & Wetherden | Wetherden, Haughley | 2025-06-17 | 2024-07-06
Mid Suffolk | Helmingham & Coddenham | Coddenham, Gosbeck, Crowfield, Pettaugh, Framsden, Helmingham, Ashbocking | 2025-06-25 | 2025-07-08
Mid Suffolk | Hoxne | Syleham, Wingfield, Hoxne, Denham (East), Horham, Athelington, Redlingfield | 2025-06-20 | 2025-07-08
Mid Suffolk | Mendlesham | mendlesham, Wickham Skeith, Cotton | 2025-06-27 | 2025-07-14
Mid Suffolk | Needham Market | Needham market, Badley | 2025-06-27 | 2025-07-13
Mid Suffolk | Onehouse | Buxhall, Great Finborough, Onehouse, Harleston, Shelland | 2025-07-03 | 2025-07-19
Mid Suffolk | Palgrave | Palgrave, Stuston, Brome and Oakley, Thrandeston, Yaxley | 2025-07-07 | 2024-07-23
Mid Suffolk | Rattlesden | Drinkstone, Rattlesden, Gedding, Felsham | 2025-07-14 | 2025-07-27
Mid Suffolk | Rickinghall & Walsham | Walsham le Willows, Wattisfield, Rickinghall Inferior, Rickinghall Superior, Botesdale, Hinderclay, Redgrave | 2025-07-16 | 2025-08-05
Mid Suffolk | Ringshall | Little Finborough, Combs, Battisford, Ringshall, Great Bricett | 2025-07-25 | 2025-08-18
Mid Suffolk | Stowmarket Central | split large parish Stowmarket | 2025-07-01 | 2025-07-15
Mid Suffolk | Stowmarket North | split large parish Stowmarket | 2025-07-04 | 2025-08-10
Mid Suffolk | Stowmarket South | split large parish Stowmarket | 2025-07-02 | 2025-07-26
Mid Suffolk | Stowupland | Stowupland, Creeting St Peter | 2025-07-15 | 2025-08-02
Mid Suffolk | Stardbroke & Laxfield | Stradbroke, Laxfield, Wilby | 2025-07-22 | 2025-08-10
Mid Suffolk | The Stohams | Stonham Parva, Stonham Earl, Creeting St Mary, Stonham Aspal | 2025-07-08 | 2025-07-22
Mid Suffolk | Thurston & Hessett | Thurston, Beyton, Hessett | 2025-07-11 | 2025-08-03
Mid Suffolk | Wetheringsett | Braiseworth, Stoke Ash, Thwaite, Wetherinsett cum Brockford, Mickfield, Thorndon, Occold | 2025-07-30 | 2025-08-12
Mid Suffolk | Woolpit | Woolpit | 2025-07-30 | 2025-08-11
Mid Suffolk | Worlingworth | Rishangles, Bedingfield, Southolt, Worlingworth, Brundish, Tannington, Bedfield, Monk Soham, Kenton, Ashfield cum Thorpe | 2025-07-29 | 2025-08-16
West Suffolk
West Suffolk | Abbeygate | split large parish Bury St Edmunds | 2025-08-07 | 2025-08-31
West Suffolk | All Saints | Split large parish Newmarket | 2025-08-20 | 2025-09-08
West Suffolk | Bardwell | Barnham, Euston, Fakenham Magna, Honington, Sapiston, Bardwell, Coney Weston | 2025-08-28 | 2025-09-14
West Suffolk | Barningham | Knettishall, Hopton, Thelnetham, Market Weston, Barningham, Hepworth | 2025-08-27 | 2025-09-13
West Suffolk | Barrow | Denham (West), Barrow, The Saxhams, Westley | 2025-08-01 | 2025-08-19
West Suffolk | Brandon East | Santon Downham, Elevden, Brandonpart | 2025-08-08 | 2025-09-07
West Suffolk | Brandon West | split large parish Brandon | 2025-07-31 | 2025-08-23
West Suffolk | Cavendish | Denston, Stansfield, Hawkedon, Brockly, Cavendish, Poslingford | 2025-08-12 | 2025-08-30
West Suffolk | Chedburgh | Chevington, Chedburgh, Whepstead, Rede, Hawstead | 2025-08-19 | 2025-09-07
West Suffolk | Clare | Clare | 2025-08-27 | 2025-09-15
West Suffolk | Eastgate | split large parish Bury St Edmunds | 2025-08-05 | 2025-08-20
West Suffolk | Eriswell & The Rows | Beck Row, Holywell Row, KennyHill, Eriswell, Mildenhallpart | 2025-08-11 | 2025-09-16
West Suffolk | Exning | Exning | 2025-08-01 | 2025-08-18
West Suffolk | Fornham | Fornham All Saints, Fornham St Genivieve, Fornham St Martin | 2025-08-07 | 2025-09-03
West Suffolk | Great Barton | Great Barton | 2025-08-26 | 2025-09-14
West Suffolk | Great Heath | split large parish Mildenhall | 2025-08-01 | 2025-08-30
West Suffolk | Haverhill East | split large parish Haverhill | 2025-08-19 | 2025-09-20
West Suffolk | Haverhill North | split large parish Haverhill | 2025-09-02 | 2025-09-29
West Suffolk | Haverhill South | split large parish Haverhill | 2025-09-18 | 2025-10-15
West Suffolk | Haverhill West | split large parish Haverhill | 2025-08-27 | 2025-09-23
West Suffolk | Horringer & Whelnetham | Ickworth, Horringer, Nowton, Great Welneatham, Little Welneatham | 2025-09-12 | 2025-10-01
West Suffolk | Hundon | Stradishall, Hundon, Stoke by Clare, Wixoe | 2025-09-22 | 2025-10-11
West Suffolk | Hundon (Biennial cycle Gullies only) | Stradishall, Hundon, Stoke by Clare, Wixoe | 2026-02-27 | 2026-03-11
West Suffolk | Iceni | Icklingham, Tuddenham, Cavenham, Higham (West), Gazeley | 2025-09-04 | 2025-09-20
West Suffolk | Iceni (Biennial Cycle Gullies only) | Icklingham, Tuddenham, Cavenham, Higham (West), Gazeley | 2026-02-27 | 2026-03-11
West Suffolk | Ixworth | Ixworth Thorpe, Ixworth | 2025-09-09 | 2025-09-23
West Suffolk | Ixworth (Biennial Cycle Gullies only) | Ixworth | 2026-03-02 | 2026-03-14
West Suffolk | Kedington | Kedington, Barnadiston, Haverhillpart | 2025-09-12 | 2025-09-24
West Suffolk | Kedington (Biennial Cycle Gullies only) | Kedington | 2026-03-03 | 2026-03-16
West Suffolk | Lakenheath | Lakenheath, Lords Walk, Eleveden, Sedge Fen, Eriswell and Little Eriswell | 2025-09-15 | 2025-09-30
West Suffolk | Lakenheath (Biennial Cycle Gullies only) | Lakenheath | 2026-03-05 | 2026-03-24
West Suffolk | Manor | Freckenham, Worlington, Barton Mills | 2025-09-19 | 2025-10-07
West Suffolk | Manor (Biennial Cycle Gullies only) | Manor | 2026-03-13 | 2026-03-25
West Suffolk | Market | split large parish Mildenhall | 2025-09-26 | 2025-10-15
West Suffolk | Market (Biennial Cycle Gullies only) | Market | 2026-03-16 | 2026-03-29
West Suffolk | Minden | split large parish Bury St Edmunds | 2025-09-05 | 2025-09-20
West Suffolk | Minden (Biennial Cycle Gullies only) | Minden | 2026-03-18 | 2026-04-04
West Suffolk | Moreton Hall | split large parish Bury St Edmunds | 2025-09-09 | 2025-10-07
West Suffolk | Moreton Hall (Biennial Cycle Gullies only) | Moreton Hall | 2026-03-03 | 2026-03-25
West Suffolk | Northgate | split large parish Bury St Edmunds | 2025-09-26 | 2025-10-12
West Suffolk | Pakenham | Timworth, Ampton, Lillte Livermere, Great Livermere, Troston, Honington, Pakenham | 2025-09-01 | 2025-10-15
West Suffolk | Risby | Lackford, Risby, Hengrave, Flempton, West Stow, Wordwell, Culford, Ingham | 2025-09-03 | 2025-09-17
West Suffolk | Risby (Biennial Cycle Gullies only) | Risby | 2026-03-24 | 2026-04-06
West Suffolk | Red Lodge | Red Lodge, Heringswell | 2025-09-08 | 2025-09-30
West Suffolk | Red Lodge (Biennial Cycle Gullies only) | Red Lodge, Heringswell | 2026-03-26 | 2026-04-11
West Suffolk | Risbygate | split large parish Bury St Edmunds | 2025-09-19 | 2025-10-05
West Suffolk | Risbygate (Biennial Cycle Gullies only) | split large parish Bury St Edmunds | 2026-03-26 | 2026-04-11
West Suffolk | Rougham | Rushbrook with Rougham, Bradfield St George, Bradfield St Clare, Bradfield Combust with Stanningfield | 2025-09-24 | 2025-10-08
West Suffolk | Rougham (Biennial Cycle Gullies only) | Rushbrook with Rougham, Bradfield St George, Bradfield St Clare, Bradfield Combust with Stanningfield | 2026-03-16 | 2026-03-29
West Suffolk | Severals | split large parish Newmarket | 2025-09-29 | 2025-10-19
West Suffolk | Severals (Biennial Cycle Gullies only) | split large parish Newmarket | 2026-03-18 | 2026-04-06
West Suffolk | South | Kentford, Moulton,Dalham | 2025-10-06 | 2025-10-25
West Suffolk | Southgate | split large parish Bury St Edmunds | 2025-10-14 | 2025-11-05
West Suffolk | St Marys | split large parish Newmarket | 2025-10-27 | 2025-11-17
West Suffolk | St Olaves | split large parish Bury St Edmunds | 2025-09-30 | 2025-10-18
West Suffolk | Stanton | Stanton | 2025-10-07 | 2025-10-25
West Suffolk | Westgate West | split large parish Bury St Edmunds | 2025-10-14 | 2025-11-02
West Suffolk | Wickhambrook | Lidgate, Ousden, Hargrave, Depden, Wickhambrook | 2025-10-22 | 2025-11-10
West Suffolk | Withersfield | Cowlinge, Great Bradley, Little Bradley, Little Thurlow, Great Thurlow, Great Wratting, Little Wratting, Withersfield | 2025-10-06 | 2025-10-25
East Suffolk
East Suffolk | Aldeburgh | Snape, Friston, Aldeburgh, Knodishall, Aldringham cum Thorpe | 2025-10-14 | 2025-11-11
East Suffolk | Beccles North | split large parish Beccles | 2025-10-03 | 2025-10-28
East Suffolk | Beccles South | split large parish Beccles | 2025-10-17 | 2025-11-09
East Suffolk | Blything | Spexhall, Westhall, Holton, Sotherton, Blyford, Wangford with Henham | 2025-10-08 | 2025-10-29
East Suffolk | Bungay | Bungay | 2025-10-20 | 2025-11-12
East Suffolk | Carlton | Oulton Broad (part), Lowestoft (part) | 2025-10-01 | 2025-10-26
East Suffolk | Carlton Colvlle | Carlton Colville | 2025-10-15 | 2025-11-18
East Suffolk | Deben | Sutton, Shottisham, Hollesley, Boyton, Alderton, Bawdsey, Ramsholt | 2025-11-06 | 2025-11-24
East Suffolk | Felixstowe East | split large parish Felixstowe | 2025-11-13 | 2025-12-01
East Suffolk | Felixstowe North | split large parish Felixstowe | 2025-11-20 | 2025-12-03
East Suffolk | Felixstowe South | split large parish Felixstowe | 2025-11-24 | 2025-12-15
East Suffolk | Felixstowe West | split large parish Felixstowe | 2025-10-30 | 2025-11-12
East Suffolk | Framlingham | Dennington, Saxstead, Framlingham, Kettleburgh, Earl Soham, Brandeston,Hoo, Monewden, Crettingham | 2025-11-03 | 2025-11-24
East Suffolk | Fynn Valley | Swilland, Witnesham, Westerfield, Tuddenham St Martin, Playford, Rushmere St Andrew | 2025-11-13 | 2025-11-30
East Suffolk | Grundisburgh | Otley, Clopton, Debach, Boulge, Bredfield, Burgh, Grudisburgh, Culpho | 2025-11-19 | 2024-12-07
East Suffolk | Gunton & Corton | Corton, Lowestoft (part) | 2025-10-31 | 2025-11-25
East Suffolk | Hatcheston | Badingham, Bruisyard, Rendham, Swefling, Cransford, Great Glemham, Parham, Stratford St Andrew, Farnham, Little Glemham, Marlesford, Hacheston, Letheringham, Easton | 2025-11-14 | 2025-12-03
East Suffolk | Halesworth | Halesworth | 2025-11-24 | 2025-12-15
East Suffolk | Harbour | split large parish Lowestoft | 2025-10-29 | 2025-11-19
East Suffolk | Kesgrave East | split large parish Kesgrave | 2025-11-10 | 2025-11-23
East Suffolk | Kesgrave West | split large parish Kesgrave | 2025-11-12 | 2025-11-24
East Suffolk | Kessingland | Kessingland, Gisleham | 2025-11-13 | 2025-12-10
East Suffolk | Kirk | split large parish Lowestoft | 2025-11-03 | 2025-11-18
East Suffolk | Kirton | Waldringfield, Newbourne, Hemley, Kirton, Falkenham, Stratton Hall, Bucklesham, Levington | 2025-11-07 | 2025-11-23
East Suffolk | Leiston | Middleton, Theberton, Leiston | 2025-11-12 | 2025-12-09
East Suffolk | Lothingland | Lound, Somerleyton, Ashby and Herringfleet, Blundeston, Flixton(east), Oulton(part) | 2025-12-04 | 2025-12-21
East Suffolk | Martlesham | Martlesham | 2025-12-10 | 2026-01-14
East Suffolk | Melton | Melton, Ufford, Bromeswell, Sutton Heath | 2025-11-26 | 2025-12-10
East Suffolk | Nacton & Purdis Farm | Purdis Farm, Foxhall, Brightwell, Nacton | 2025-12-01 | 2025-12-14
East Suffolk | Normaston | split large parish Lowestoft | 2025-12-03 | 2024-12-24
East Suffolk | Orford & Eyke | Blaxhall, Campsey Ash, Tunsall, Iken, Sudbourne, Orford, Chillesford, Wantisden, Eyke, Capel St Andrew, Butley, Gedgrave | 2025-12-15 | 2026-01-03
East Suffolk | Oulton | Oultonpart, Oulton Broadpart | 2025-12-23 | 2026-01-14
East Suffolk | Oulton Broad | Oulton Broadpart | 2025-12-04 | 2025-12-27
East Suffolk | Pakefield | split large parish Lowestoft | 2025-12-16 | 2026-01-04
East Suffolk | Peasonhall & Yoxford | Cediston, Linstead Parva, Linstead magna, Cratfield, Huntingfield, Cookley, Ubbeston, Walpole, Heveningham, Peasenhall, Sibton, Yoxford | 2025-12-24 | 2026-01-20
East Suffolk | Rendlesham | Rendlesham | 2025-12-01 | 2025-12-20
East Suffolk | Saxmundham | Kelsale cum Carlton, Saxmundham, Benhall, Sternhall | 2025-12-09 | 2026-01-03
East Suffolk | Southwold & Reydon | Southwold, Reydon | 2026-01-05 | 2026-01-26
East Suffolk | St Margarets North | split large parish Lowestoft | 2025-01-15 | 2026-02-17
East Suffolk | The Saints | South Elmham:- St Mary, St Cross, St Margaret, St Peter, St Michael, All Saints and St Nicholas Ilketshall:- St John, St Andrew, St Lawrence, St Margaret Rumburgh, Wissett | 2025-01-05 | 2026-01-26
East Suffolk | The Trimleys | Trimley St Martin, Trimley St Mary | 2026-01-15 | 2026-02-11
East Suffolk | Tower | Rushmere St Andrew (part) | 2026-01-09 | 2026-02-04
East Suffolk | Wainford | Mettingham, Shipmeadow, Barsham, Ringsfield, Redisham, Weston, Shadingfield, Ellough, Willingham St Mary, Sotterley, Mutford | 2026-01-26 | 2026-02-16
East Suffolk | Wenhaston & Westleton | Wehaston with Malls, Bramfield, Thorington, Blythburgh, Walberswick, Dunwich, Westleton, Darsham | 2025-12-23 | 2026-01-14
East Suffolk | Whitton North | Lowestoft (part), Oulton Broad (part) | 2026-01-05 | 2026-02-01
East Suffolk | Wickham Market | Charsfield, Dallinghoo, Wickham Market, Pettistree | 2026-01-21 | 2026-02-09
East Suffolk | Woodbridge | Hasketon, Woodbridge, Great Bealings, Little Bealings | 2026-01-02 | 2026-02-02
East Suffolk | Worlingham | Worlingham, North Cove, Barnby | 2026-01-22 | 2026-02-17
East Suffolk | Wrentham | Brampton with Stoven, Uggeshall, Frostenden, Wrentham, Henstead with Hulver street, Rushmere, Benacre, Covehithe, South Cove | 2026-01-29 | 2026-02-17
Ipswich
Ipswich | Alexandra | split large parish Ipswich | 2026-02-06 | 2026-03-01
Ipswich | Alexandra (Biennial Cycle Gullies only) | Alexandra | 2026-03-26 | 2026-04-12
Ipswich | Bixley | split large parish Ipswich | 2026-02-18 | 2026-03-10
Ipswich | Bixley (Biennial Cycle Gullies only) | Bixley | 2026-02-26 | 2027-03-11
Ipswich | Bridge | split large parish Ipswich | 2026-02-02 | 2026-02-22
Ipswich | Bridge (Biennial Cycle Gullies only) | Bridge | 2026-03-02 | 2026-03-15
Ipswich | Castle Hill | split large parish Ipswich | 2026-02-11 | 2026-03-02
Ipswich | Castle Hill (Biennial Cycle Gullies only) | Castle Hill | 2026-03-04 | 2026-03-16
Ipswich | Gainsborough | split large parish Ipswich | 2026-02-19 | 2026-03-09
Ipswich | Gainsborough (Biennial Cycle Gullies only) | Gainsborough | 2026-03-05 | 2026-03-17
Ipswich | Gipping | split large parish Ipswich | 2026-02-05 | 2026-03-01
Ipswich | Gipping (Biennial Cycle Gullies only) | Gipping | 2026-03-06 | 2026-03-21
Ipswich | Holywells | split large parish Ipswich | 2026-02-26 | 2026-03-14
Ipswich | Holywells (Biennial Cycle Gullies only) | Holywells | 2026-03-10 | 2026-03-23
Ipswich | Priory Heath | split large parish Ipswich | 2026-02-18 | 2026-03-09
Ipswich | Priory Heath (Biennial Cycle Gullies only) | Priory Heath | 2026-03-12 | 2026-03-31
Ipswich | Rushmere | split large parish Ipswich | 2026-02-05 | 2026-02-25
Ipswich | Rushmere (Biennial Cycle Gullies only) | Rushmere | 2026-03-20 | 2026-04-01
Ipswich | Sprites | split large parish Ipswich | 2026-02-16 | 2026-03-04
Ipswich | Sprites (Biennial Cycle Gullies only) | Sprites | 2026-03-03 | 2026-03-17
Ipswich | St John | split large parish Ipswich | 2026-02-23 | 2026-03-14
Ipswich | St Margarets South | split large parish Ipswich | 2026-02-06 | 2026-02-25
Ipswich | St Margarets South (Biennial Cycle Gullies only) | St Margarets South | 2026-03-06 | 2026-03-21
Ipswich | Stoke Park | split large parish Ipswich | 2026-02-16 | 2026-03-08
Ipswich | Stoke Park (Biennial Cycle Gullies only) | Stoke Park | 2026-03-10 | 2026-03-24
Ipswich | Westgate East | split large parish Ipswich | 2026-02-25 | 2026-03-15
Ipswich | Westgate East (Biennial Cycle Gullies only) | split large parish Ipswich | 2026-03-13 | 2026-03-25
Ipswich | Whitehouse | split large parish Ipswich | 2026-02-02 | 2026-02-18
Ipswich | Whitehouse (Biennial Cycle Gullies only) | split large parish Ipswich | 2026-03-16 | 2026-03-31
Ipswich | Whitton South | split large parish Ipswich | 2026-02-09 | 2026-03-02
Ipswich | Whitton South (Biennial Cycle Gullies only) | Whitton South | 2026-03-20 | 2026-04-04
A12 and A140 are carried out as end to end routes, due to specialist traffic management
N/A | A12 and A140 | Multiple Parishes | 2025-04-01 | 2025-07-12